## Rollout Tracker
Dashlane Rollout Plan — Progress Tracker
Make your own copy of this sheet (File > Make a copy) to track your organization's rollout progress.
Phase | Task Name | Description | Status | Status Notes | Start Week | End Week | Action Items | Why It Matters | Metrics to Track / Target Goal | Dashlane Documentation
Phase 1: Foundation & Identity Integration | Invite at least one additional admin | Access the Dashlane Admin Console and navigate to the Credential Risk Detection insights. Set up Credential Risk Detection. | Not Started |  | 1 | 2 | N/A | N/A | Additional admin has been invited, accepted, and created a Dashlane account | Documentation
Phase 1: Foundation & Identity Integration | Configure Confidential Single Sign-On (SSO) | Integrate Dashlane with your Identity Provider (IdP) such as Okta, Microsoft Entra ID (Azure AD), Ping Identity, or Google Workspace using SAML 2.0. | Not Started |  | 1 | 2 | Enable Just-In-Time (JIT) provisioning or SCIM directory sync to automate onboarding and offboarding. | Confidential SSO allows users to access vaults seamlessly without memorizing separate Master Passwords, eliminating weak/exposed password risks. | N/A | Documentation
Phase 1: Foundation & Identity Integration | Deploy Risk Detection – Establish Risk Baseline | Access the Dashlane Admin Console and navigate to the Credential Risk Detection insights. Set up Credential Risk Detection. | Not Started |  | 1 | 2 | Access insights to understand current risk profile before prompting users to change habits. | Establishes a security baseline to track future improvements. | Number of users with compromised and weak credentials; high risk domains where compromised and weak credentials are being used | Documentation
Phase 1: Foundation & Identity Integration | Prepare and Communicate Migration Plan | Create a communication plan (announcement email) and schedule training sessions for the target group. | Not Started |  | 1 | 2 | Distribute announcement 1-3 days prior to sending invitation; coordinate training with deployment. | Proactive communication ensures users understand the 'why' and expected timeline, reducing friction. | N/A | Documentation
Phase 1: Foundation & Identity Integration | Invite first group of users | Add first users to Dashlane consisting of 5-10% of the user base. | Not Started |  | 1 | 2 | Invite initial pilot group to validate onboarding and login processes. | Validates system rollout and surfaces early questions before wider enterprise deployment. | Employees who have accepted the invite and become Dashlane vault users; users who have at least 5 passwords saved in Dashlane | Documentation
Phase 2: Active Phishing Defense & Optimization | Turn on AI Phishing Alerts | Turn on AI Phishing Alerts in the admin policies. | Not Started |  | 3 | 4 | Activate real-time protection against credential harvesting. | Analyzes web structures locally in real time, blocking autofill/pasting on unrecognized, spoofed, or suspicious domains. | N/A | Documentation
Phase 2: Active Phishing Defense & Optimization | Conduct a Week-One 'False Positive' Review | Audit administrative console logs exactly one week after enabling Phishing Alerts. | Not Started |  | 3 | 4 | Audit logs and add verified internal or partner domains to the corporate allowlist. | Mitigates alert fatigue, ensuring employees take legitimate phishing warnings seriously. | N/A | Documentation
Phase 2: Active Phishing Defense & Optimization | Prepare and Communicate Migration Plan (Rollout) | Create a communication plan (announcement email) and schedule training sessions for the target group. | Not Started |  | 3 | 4 | Distribute announcement 1-3 days prior to sending invitation; coordinate training with deployment. | Ensures the next tier of users understand the rollout process and expected timelines. | N/A | Documentation
Phase 2: Active Phishing Defense & Optimization | Invite additional users | Invite additional users to Dashlane, targeting 100% of the purchased seats. | Not Started |  | 3 | 4 | Expand invitation pool to cover all purchased enterprise seats. | Commences general rollout following the successful pilot phase. | Employees who have accepted the invite and become Dashlane vault users; users who have at least 5 passwords saved in Dashlane | Documentation
Phase 3: Schedule user Risk Alerts & Notifications | Turn on in-browser Credential Risk Alerts | Alert logged-out and non-vault users on compromised, weak, and/or reused credentials. | Not Started |  | 5 | 5 | Turn on in-browser pop-up alerts for logged-out and non-vault users. | Prompts users to start using Dashlane and update high-risk credentials. | N/A | Documentation
Phase 3: Schedule user Risk Alerts & Notifications | Turn on in-browser Credential Risk Alerts | Alert logged-in vault users on compromised, weak, and/or reused credentials. | Not Started |  | 6 | 7 | Turn on in-browser pop-up alerts for logged-in vault users. | Cleans up legacy, easily crackable passwords without generating administrative friction. | N/A | Documentation
Phase 3: Schedule user Risk Alerts & Notifications | Turn on Risk Notifications sent through Slack | Schedule Slack notifications for logged-in vault users: compromised, weak, and/or reused. | Not Started |  | 8 | 8 | Schedule Slack notifications for logged-in vault users: compromised, weak, and/or reused. | Halts potential lateral movement by preventing attackers from pivoting from personal site breaches to corporate infrastructure. | N/A | Documentation
Phase 4: SIEM Integration & Training Automation | Automate Just-In-Time Coaching with KnowBe4 (if applicable) | Configure integration between Dashlane events, your SIEM, and KnowBe4's User Event API. | Not Started |  | 9 | 12 | Phishing Play: auto-enroll user in training if AI Phishing warning is ignored. Compromised Credential Play: trigger automated email sequence for bypassed alerts. | Automates security remediation and coaching directly tied to real-time user risk events. | N/A | Documentation
Phase 4: SIEM Integration & Training Automation | Configure SIEM Integration | Export Dashlane activity logs to your SIEM tool (Splunk / Microsoft Sentinel). | Not Started |  | 9 | 12 | Integrate SIEM tool following the Dashlane integration guide. | SOC teams gain centralized visibility into critical events like bypassed phishing warnings. | N/A | Documentation
Phase 4: SIEM Integration & Training Automation | Enable Vault Enforcement to Enforce Adoption (Available July 13) | Add 3-5 domains common in the business to the Vault Enforcement section, or review the risk detection dashboard. | Not Started |  | 9 | 12 | Enforce Dashlane usage on business-critical sites. | Ensures users log in to Dashlane and see password risk nudges to change passwords. | Employees who have become Dashlane vault users; users who have at least 5 passwords saved in vault | Documentation
KPI Tracking | Enterprise Password Health Score | Continuous performance goal checking | Not Started |  | Monthly | Ongoing | Track overall password strength across organization | Maintains organizational security posture | > 85% | Documentation
KPI Tracking | Compromised Password Count | Continuous performance goal checking | Not Started |  | Bi-weekly | Ongoing | Track and eliminate compromised passwords | Minimizes active exposure from external breaches | 0 | Documentation
KPI Tracking | Vault Adoption Rate | Continuous performance goal checking | Not Started |  | Monthly | Ongoing | Track deployment penetration across employees | Ensures full return on investment and coverage | 100% of eligible employees
KPI Tracking | Training Enrollment Latency | Continuous performance goal checking | Not Started |  | Real-time | Ongoing | Track time from risk event to coaching enrollment | Ensures training relevancy immediately following risky behavior | < 2 hours from risk event trigger
Maintenance | Monthly Review | Continuous governance | Not Started |  | Monthly | Ongoing | Analyze SIEM reports to identify serial offenders who ignore nudges. | Routes repeat offenders to managers or targeted security training. | N/A
Maintenance | Quarterly Audit | Continuous governance | Not Started |  | Quarterly | Ongoing | Audit the domain allowlist. | Removes decommissioned testing environments or inactive external services. | N/A
Maintenance | Annual Review | Continuous governance | Not Started |  | Annually | Ongoing | Review Identity Provider group mapping in SCIM. | Ensures appropriate default vault permissions for new organizational roles. | N/A